# Moon - Project Plan

Name: Mishkatuz Zannat Moon · Student ID: 385411 · Unit: HIT339 Group Project (library system)

## What I'm responsible for

I built three things on top of our Assignment 2 library system, plus the paperwork for them. All three are merged into main (pull requests #2 to #5).

- Read-only REST API: lets anyone look up items, items by ID or code, categories and the system status. It's GET only (no changing data), and it has an OpenAPI file and a docs page.

- CSV importer: the Admin uploads a CSV file, the system checks it and shows a preview, and only then does it save. Bad rows and duplicates are listed and never saved.

- Manager reports and export: borrowing, fines and inventory reports with a date filter, which can be downloaded as CSV or PDF.

- Documents: my requirements list, and notes on the API, importer and reports. They're all in docs/moon/.

Not mine: the branch model (Taief) and the kiosk (Achi).

## My tasks and hours

I had 10 tasks and planned 60 hours in total, and all of them are finished. The hours in the "Actual" column are estimates. I didn't track my time as I worked, so I set them equal to what I planned.

| Task | What it is | Planned hours | Actual hours (estimate) | Status | Depends on |
| --- | --- | --- | --- | --- | --- |
| MOON-01 | Read-only API: items, by ID or code, categories, status, errors | 8 | 8 | Done, merged | Base catalogue |
| MOON-02 | OpenAPI file and API docs page | 2 | 2 | Done, merged | MOON-01 |
| MOON-03 | CSV importer: upload, checks, preview, confirm | 10 | 10 | Done, merged and tested | Base catalogue, Admin role |
| MOON-04 | Reports: borrowing, fines and inventory with date filter | 8 | 8 | Done, merged and tested | Loans and fines data, Manager role |
| MOON-05 | CSV and PDF export | 6 | 6 | Done, merged and tested | MOON-04 |
| MOON-06 | Requirements, acceptance criteria and traceability | 4 | 4 | Done | MOON-01 to 05 |
| MOON-07 | Notes for the API, importer and reports | 3 | 3 | Done | MOON-01 to 05 |
| MOON-08 | Testing, screenshots and evidence | 5 | 5 | All 33 tests passed, with screenshots as evidence | MOON-01 to 05 |
| MOON-09 | Project plan and integration diagrams (with Taief) | 8 | 8 | Done: plan section, integration diagrams and user journeys | Taief's plan |
| MOON-10 | Meetings, merge fixes and final review | 6 | 6 | Pull requests merged | All of the above |

## Schedule and milestones

The building is finished. I tested the features, wrote the documents and drew the diagrams.

- Done: API, importer, reports and export built, tested in the browser and merged into main.

- Done: requirements and notes written.

- Done: I ran the whole test plan, including building the project and issuing and returning a loan. All 33 tests passed.

- Done: wrote my project plan and portfolio sections, including the integration diagrams and user journeys.

## Dependencies and risks

| What could go wrong | What happens | What I did |
| --- | --- | --- |
| The repo tracks bin/, obj/, .vs/ and the database files | Pull requests get messy and can clash | My branches avoid them. The fix is to stop tracking them and add a .gitignore |
| The site can't be built while it's still running | The build fails because the program file is locked | Stop the site first, then build (this happened to me once) |
| The API docs page needs internet for its Swagger files | The page looks blank offline | The OpenAPI file at /openapi/v1.json works offline, so it can be shown in the demo instead |
| My hours weren't tracked | My hours are only estimates | I say clearly in the plan that they're estimates |

## AI Acknowledgement:

I used Claude to help me with my part of the assignment.